## Mar19
Highlight Report: St Austell Bay Economic Forum (SABEF) Coastal Communities Fund Project
Reporting Period | 24.01.2019 - 26.03.2019 | Overall Status this Period | G
Submitted by | Nikki Hotchin | RAG Status last Period | G
Reporting to: | SABEF Executive Board
Workstreams | RAG Status | Comments
Masterplan & Design | G | In progress
Greening | G | Garden Festival date agreed - June 22nd 2019
Ceramics/Art | G | Whitegold Festival date agreed - September 21st 2019
Engagement/Marketing/PR/Events | G | In progress
Governance/Finances | G | In progress
Project Delivery, Monitoring & Evaluation | G | In progress
Website | G | In progress
This Period Key Achievements
Recruitment - Ceramic/Greening Curators/Project Manager/PR/Events and Greening Support resources - Approved at SABEF Exec Board 23.01.19
Masterplan Phase 1 Draft - Complete - Approved at SABEF Exec 23.01.19
Website - Design/Technical build/Content - Progress presented to SABEF Exec today
Design/Plans - Draft high level plans - complete. Rollout and Presentations made to; CoC/Town Council/Community Network Panel. Links made with stakeholders/partner organisations to progress and discuss. E.g. Kneehigh/TC/CC/WRP. HIghways Links made to progress planning permissions and to establish constraints with regards to roundabout planting.
Ceramic Curators/Experts/PMgrs commissioned to progress Whitegold/Ceramics Prize/Clay Exchange
Whitegold Activities - THS Parasite Training Days (Creative Front) and The Hive workshop event fully supported by the team
Masterplan Phase 1 roll out - complete
Garden Festival kick off meeting complete with actions underway to progess and community engagement commenced
Engagement activities with the wider community commenced/working with Cornwall VSF/Town Council/CC/schools & Colleges etc...
GWG meeting held - 27.02.19
Project team mobilised and tasks/actions underway
Review of GDPR compliance taken place and updated where appropriate
Governance processes agreed
Next Period Key Activities
Wider community activities/workshops/roadshows to commence
A391/A390 "as built" Drawings to be obtained/Planning permission expectations to be explored/links with Cormac Street Works/Cormac Estimating/Highways to be made
Master plans to be prioritised.
Detailed plans to be finalised
WildFlower Consultation to take place - April 3rd by Pictorial Meadows
Timelines/Activities/Tasks/Milestones to be worked up - GANTT in progress
Garden Festival/Whitegold Festival plans to be progressed/Promotional activities to be complete.
Contractor tender process to commence/ITT for garden projects (where applicable)/Cormac accredited contractors list to be explored.
Ceramic Artist briefs to be complete
Explore university study of the project re: evaluation/outcomes/impact

## Jan19
Highlight Report: St Austell Bay Economic Forum (SABEF) Coastal Communities Fund Project
Reporting Period | 07.11.2018 to 23.01.2019 | Overall Status this Period | G
Submitted by | Nikki Hotchin | RAG Status last Period | n/a
Reporting to: | SABEF Executive Board
Workstreams | RAG Status | Comments
Masterplan & Design | G | Underway - See below
Garden Festival | G | Provisional date in the diary for next year - June 22nd 2019
Whitegold Event | G | Provisional date in the diary for next year - September 21st 2019
Engagement/Marketing/PR | G | Underway - See below
Governance/Accountancy | G | Underway - See below
Project Delivery Monitoring & Evaluation | G | Underway - See below
Website | G | New development/design team in place to drive the website forward
This Period Key Achievements
Recruitment - Ceramic/Greening Curators/Project Manager/PR/Events and Greening Support resources proposed and awaiting board approval today.
Funding - 01st and 2nd draw down complete
Masterplan Phase 1 Draft - Completed, awaiting approval by the Exec Board and roll out schedule in place
Website - New development/design team in place, Discovery meeting taken place, Refresh underway.
Establishment Secured - Unit 6 at the Market House Secured from 01st March as a Project Hub/Community Engagement Hub. Wheal Eliza Nursery being explored with CCouncil (Ongoing) supported by TCouncil
Design team established
Townscape Heritage Board representation established/Links with Andrew Richards re Parasite Training Day and Ceramic Signs in Town
Cultural Partnership representation established
Horizon Scanning process in place - The process by which to identify and capture opportunities Funding/Grants/Bids/Events/Other
KneeHigh Meeting taken place to connect the project with walking stories
Arts Council Presentation delivered to share the CCF vision
Links made with Botanist Experts - Andrew Ormerod
Cormac meetings taken place to establish links
Project team established/Meetings Scheduled
Next Period Key Activities
Masterplan Phase 1 roll out - to be completed - Schedule in place
Project/Resource plan development stage
Masterplan Phase 2 design stage
Engagement activities with the wider Community to commence working with Cornwall VSF
Set up Unit 6/Explore opportunities revenue opportunities
Mobilise teams and wider teams