## Nov19
Highlight Report: St Austell Bay Economic Forum (SABEF) Coastal Communities Fund Project
Reporting Period | 26.09.19 to 27.11.19 | Overall Status this Period | G
Submitted by | Nikki Hotchin | RAG Status last Period | G
Reporting to: | SABEF Executive Board
Workstreams | RAG Status | Comments
Masterplan Delivery, Monitoring & Evaluation | G
Green Project | G
Whitegold Project | G
Communication/Engagement/Events | G
Governance/Finances | G
Website | G
This Period Key Achievements
Discussions underway and plans taking shape with Matt James and the Eden Horticultural Students regarding the planting schemes at the Northern end of the train station. Working with the "Friends of The St Austell Railway Station"
Other funding streams are being explored to support the continuation of key projects. For e.g., Clean Cornwall/THI match funding and more strategic opportunities.
Generating revenue streams via the website with businesses and tourist destinations is underway. Preliminary, high level research has taken place to see how our competitors in the market address this. Results tbc.
Delivery of all projects with partner organisations is progressing.
Planning Consultant (Situ8) engaged. There will be planning concerns/requirements for a number of project locations for e.g. Pinetum. Consultation will be in two parts; firstly to review the full set of projects and to confirm which of them will need permissions and what type (e.g. certificate of lawfulness/full planning permission etc) and secondly to take those applicable projects forward to the submission of the relevant applications. Michael Hawes is managing the process.
C/C/Cormac/GI4G hand over of works and plans underway.
Whitegold Festival - 19th September 2020 - Plans underway
Garden Festival - 27th June 2020 - Plans underway
International Ceramic's Prize - PR underway for both 2019 winners and 2020 Prize (invitation to apply) - Ceramics Review publication from December 9th (Jan edition)
Art commissions have been invited for 4 sites within the Town Centre - The review panel, made up of number of representatives from our partner organisations, are due to meet next week to agree on the finalists.
PR specialists commissioned to drive our PR campaign locally, nationally and internationally
Brickfields Project extended to end of October 2020 and planning is underway to expand on the Brickfields concept to increase community engagement.
Kiln now at the Market House - Awaiting specialist assessment and possible requirement of 3 phase power. Discussions invited with the Whitegold team regarding how we now extend the use of this to international artists in residence and various local ceramic/potter experts to help make this a community kiln.
Rebranding presentation will be used as a tool to generate more local engagement activities - PR Strategy underway to inform this. Marketing Strategy underway.
MHCLG twice yearly monitoring report was submitted in October
Engagement continues - SABEF is represented at the NHS England Health New Towns Initiative - West Carclaze Garden Village/THI Strategic Board/Friends of the St Austell Railway Station/St Austell Community Connections (reaching out and working with the wider communities)/Working with Volunteer Cornwall/Cornwall Council Project Managers to progress ideas/Meeting with local groups and individuals to discuss specific local plans and identify how we can work together. SABEF are working across multiple local initiatives to join up and complement other projects where applicable for e.g. Town Council/THI
Social media/website reach increasing - plus 1000 followers on FB. Up to 2.5k unique users on the website each month. Please help us to spread the word. Website content and Social media management being assessed for a longer term/wider reaching solution as the project picks up pace. Whitegold and Garden Festival websites to be reskinned in line with the new branding and included into the main St Austell website. Working with the wider community at specific user groups, the website is now considered a single point of reference for all things St Austell and the local groups, reaching out to the clay areas, who have agreed to share information to include on the website.
Next Period Key Activities
PR activities to increase
Masterplan drawings and designs to be agreed and finalised
Garden Festival activities - Schools engagement to be underway
T/Ctre commissions to be agreed/announced
International Prize winners to be announced nationally and installation/engagement work to commence
Additional funding streams to be explored in detail

## Sept19
Highlight Report: St Austell Bay Economic Forum (SABEF) Coastal Communities Fund Project
Reporting Period | 25.07.19 to 25.09.19 | Overall Status this Period | G
Submitted by | Nikki Hotchin | RAG Status last Period | G
Reporting to: | SABEF Executive Board
Workstreams | RAG Status | Comments
Masterplan Delivery, Monitoring & Evaluation | G
Green Project | G
Whitegold Project | G
Communication/Engagement/Events | G
Governance/Finances | G
Website | G
This Period Key Achievements
Detailed plans and costings for each project approved. Pinetum Landform approved by Pinetum. Permissions approval underway with all the agencies involved.
C/C/Cormac/GI4G hand over of works and plans underway. GI4G confirmed as delivering the wildflower element along the A391 and working with the NWC
Whitegold Festival - 21st September - Done
International Ceramic Prize - 10 Finalists visited St Austell during a 2 day period with a Pit to port to tour, a visit to town, Brickfields and the Asylum finishing with a presentation by each artist at the WG Fest
Brickfields Project extended to end of October 2019
Falmouth University Kiln x1 moved to Wheal Martyn building pending work done to permanent position/ x1 confirmed as going to the Market House
WG/Library/Eden Freshers week pop up events to share our story/project - Engagement activities continue
Comms/Engagement/Events; Visit by International travel writer Meg Prater (USA) who stayed in Mevagissey and visited Wheal Martyn, Charlestown, St Austell town, Brickfields. Meg will publish a report about our story on her blog/website. A news article coming in the Times to follow on from that written in 2017 about the Clay Town. RSAB/BBC Radio Cornwall broadcasts by Dr Katie Bunnell to share news of the prize and brickfields. St Austell voice reporting on the international artists visit. Attendance at Breeze and BCB by AM raise awareness of Whitegold. A brickmaking event at CAST in Helston with Rosanna Martin and Dr Katie Bunnell including stories by Ivor Bowditch (China Clay History Society)
Social media/website reach increasing - 1000 followers on FB plus up to 2.5k unique users on the website throughout August. Please help us to spread the word
Next Period Key Activities
Progress discussions with Matt James and Eden Horticultural Students regarding the Railway station planting/Bio Diversity study
Other funding streams are being explored to support the continuation of key projects
Exploring how to generate revenue streams via the website amongst businesses and tourist destinations
PR to be explored to reach out internationally
Progress with the delivery of all projects with partner organisations

## Jul19
Highlight Report: St Austell Bay Economic Forum (SABEF) Coastal Communities Fund Project
Reporting Period | 23.05.19 to 24.07.19 | Overall Status this Period | G
Submitted by | Nikki Hotchin | RAG Status last Period | G
Reporting to: | SABEF Executive Board
Workstreams | RAG Status | Comments
Masterplan | G
Garden Project | G
Whitegold Project | G
Communication/Engagement/Events | G
Governance/Finances | G
Project Delivery, Monitoring & Evaluation | G
Website | G
This Period Key Achievements
Whitegold artist briefs underway
International Ceramic Prize Launched/Brickfields Project Underway throughout July/Aug/Sept and site confirmed as Blackpool Pit
Explore university study of the project outcomes/impact - Discussions under way led by Darren Hawkes with Eden Horticultural Students
RCS/Heligan/Library pop up events to share our story, events and garden festival
Garden Festival Successfully delivered by the team/Tree planting by Geraint Richards (Duchy Head Forrester)/Masterplans and Website on display
School suitcase competiton winner prize presentations made by the Mayor - Facilitated by Nic Andersen
C/C permissions explored/links with Cormac made - Meeting with Nigel Blackler/Cormac/Gi4G took place 30.05.19 & 05.07.19 & a follow up meeting took place on 17.07.19
Final projects proposed and awaiting SABEF Exec sign off.
Detailed plans and costings for each project is underway
Carlyon Road Bus Shelter Artist Commissioned/Approval letters sent to C/Council to commence restoration work on the shelter/T/C agree to take over maintenance following restoration and redesign
Social media/Facebook activites increasing - please help us to spread the word
Engagement activities with the wider community commenced/Cornwall VSF - "Shaping our Community" Breakout meetings commenced St Austell Futures & St Austell Connections. Met with Malcolm Brown/Jenny Moore/Sandra Heyward and Wendy Earl (Facilitated a planting review at the Railway station with Darren Hawkes/Matt James)
Next Period Key Activities
Detailed plans and costings for each project to be completed
C/C/Cormac/Gi4G hand over of works and plans
Whitegold Festival - 21st September
Ceramic Art projects to be progressed
Greening projects to be progressed

## May19
Highlight Report: St Austell Bay Economic Forum (SABEF) Coastal Communities Fund Project
Reporting Period | 27.03.19 to 22.05.19 | Overall Status this Period | G
Submitted by | Nikki Hotchin | RAG Status last Period | G
Reporting to: | SABEF Executive Board
Workstreams | RAG Status | Comments
Masterplan | G | In progress
Garden Project | G | Garden Festival date agreed - June 22nd 2019
Whitegold Project | G | Whitegold Festival date agreed - September 21st 2019
Communication/Engagement/Events | G | In progress
Governance/Finances | G | In progress
Project Delivery, Monitoring & Evaluation | G | In progress
Website | G | In progress
This Period Key Achievements
A391/A390 "as built" Drawings/Utilities plans obtained to inform masterplan
WildFlower Consultation to taken place - 3rd April - Plans agreed as part of the masterplan
Garden Festival/Whitegold Festival plans and activities underway: Garden festival - Website/social media channels/marketing materials/media releases/suitcases in place/plans underway. Whitegold - Good work on Hive- approx 716 particpants, including Prince Charles and Emma Bridgewater (Schools attended: Foxhole Primary school over two days (20/21 March) Total of 8 groups of between 20 and 30 pupils each time with support including Head Teacher. Pondhu Primary school over two days (28/29 March) Total of 4 groups of between 25 and 30 pupils each time with support. Carclaze Primary school 5 April 1 group of 30 with support.Other groups. Local “coffee” Ladies group 10 April. Group of 4 Mid Cornwall Hub (special needs) 11 April. Group of 12 with support. Group of adults with disabilities x13 with x3 support New collaboration with Crafts Council on long term up-skilling of craft work with schools in pipeline - Making Your Future - work with Brannel and Poltair schools. Clay Exchange now up and running - site being chosen in collaboration with Imerys and Eco Bos possibly Blackpool Mine Ceramics Prize launched. Public realm plans finalised with the design team. Meetings with CAST and Leech Pottery on collaborations
Masterplan Phase 1 proposed plans/prioritys/costs complete - Presented to SABEF Exec today
Website - Feedback complete - will be Live following todays meeting
HRH visit - shared our plans with HRH Duke of Cornwall
Engagement activities with the wider community commenced/working with Cornwall VSF - Shaping our community event complete
Next Period Key Activities
Whitegold artist briefs to be complete
Explore university study of the project re: evaluation/outcomes/impact
Heligan/Library pop up events to share our story and events
Planning permissions to be explored/links with Cormac Street Works/Cormac Estimating/Highways to be made - Meeting with Nigel Blackler 30.05.19
Work up project plans to deliver each project

## Mar19
Highlight Report: St Austell Bay Economic Forum (SABEF) Coastal Communities Fund Project
Reporting Period | 24.01.2019 - 26.03.2019 | Overall Status this Period | G
Submitted by | Nikki Hotchin | RAG Status last Period | G
Reporting to: | SABEF Executive Board
Workstreams | RAG Status | Comments
Masterplan & Design | G | In progress
Greening | G | Garden Festival date agreed - June 22nd 2019
Ceramics/Art | G | Whitegold Festival date agreed - September 21st 2019
Engagement/Marketing/PR/Events | G | In progress
Governance/Finances | G | In progress
Project Delivery, Monitoring & Evaluation | G | In progress
Website | G | In progress
This Period Key Achievements
Recruitment - Ceramic/Greening Curators/Project Manager/PR/Events and Greening Support resources - Approved at SABEF Exec Board 23.01.19
Masterplan Phase 1 Draft - Complete - Approved at SABEF Exec 23.01.19
Website - Design/Technical build/Content - Progress presented to SABEF Exec today
Design/Plans - Draft high level plans - complete. Rollout and Presentations made to; CoC/Town Council/Community Network Panel. Links made with stakeholders/partner organisations to progress and discuss. E.g. Kneehigh/TC/CC/WRP. HIghways Links made to progress planning permissions and to establish constraints with regards to roundabout planting.
Ceramic Curators/Experts/PMgrs commissioned to progress Whitegold/Ceramics Prize/Clay Exchange
Whitegold Activities - THS Parasite Training Days (Creative Front) and The Hive workshop event fully supported by the team
Masterplan Phase 1 roll out - complete
Garden Festival kick off meeting complete with actions underway to progess and community engagement commenced
Engagement activities with the wider community commenced/working with Cornwall VSF/Town Council/CC/schools & Colleges etc...
GWG meeting held - 27.02.19
Project team mobilised and tasks/actions underway
Review of GDPR compliance taken place and updated where appropriate
Governance processes agreed
Next Period Key Activities
Wider community activities/workshops/roadshows to commence
A391/A390 "as built" Drawings to be obtained/Planning permission expectations to be explored/links with Cormac Street Works/Cormac Estimating/Highways to be made
Master plans to be prioritised.
Detailed plans to be finalised
WildFlower Consultation to take place - April 3rd by Pictorial Meadows
Timelines/Activities/Tasks/Milestones to be worked up - GANTT in progress
Garden Festival/Whitegold Festival plans to be progressed/Promotional activities to be complete.
Contractor tender process to commence/ITT for garden projects (where applicable)/Cormac accredited contractors list to be explored.
Ceramic Artist briefs to be complete
Explore university study of the project re: evaluation/outcomes/impact

## Jan19
Highlight Report: St Austell Bay Economic Forum (SABEF) Coastal Communities Fund Project
Reporting Period | 07.11.2018 to 23.01.2019 | Overall Status this Period | G
Submitted by | Nikki Hotchin | RAG Status last Period | n/a
Reporting to: | SABEF Executive Board
Workstreams | RAG Status | Comments
Masterplan & Design | G | Underway - See below
Garden Festival | G | Provisional date in the diary for next year - June 22nd 2019
Whitegold Event | G | Provisional date in the diary for next year - September 21st 2019
Engagement/Marketing/PR | G | Underway - See below
Governance/Accountancy | G | Underway - See below
Project Delivery Monitoring & Evaluation | G | Underway - See below
Website | G | New development/design team in place to drive the website forward
This Period Key Achievements
Recruitment - Ceramic/Greening Curators/Project Manager/PR/Events and Greening Support resources proposed and awaiting board approval today.
Funding - 01st and 2nd draw down complete
Masterplan Phase 1 Draft - Completed, awaiting approval by the Exec Board and roll out schedule in place
Website - New development/design team in place, Discovery meeting taken place, Refresh underway.
Establishment Secured - Unit 6 at the Market House Secured from 01st March as a Project Hub/Community Engagement Hub. Wheal Eliza Nursery being explored with CCouncil (Ongoing) supported by TCouncil
Design team established
Townscape Heritage Board representation established/Links with Andrew Richards re Parasite Training Day and Ceramic Signs in Town
Cultural Partnership representation established
Horizon Scanning process in place - The process by which to identify and capture opportunities Funding/Grants/Bids/Events/Other
KneeHigh Meeting taken place to connect the project with walking stories
Arts Council Presentation delivered to share the CCF vision
Links made with Botanist Experts - Andrew Ormerod
Cormac meetings taken place to establish links
Project team established/Meetings Scheduled
Next Period Key Activities
Masterplan Phase 1 roll out - to be completed - Schedule in place
Project/Resource plan development stage
Masterplan Phase 2 design stage
Engagement activities with the wider Community to commence working with Cornwall VSF
Set up Unit 6/Explore opportunities revenue opportunities
Mobilise teams and wider teams